## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08
As a Quartermaster I want to review stock changes so I can ensure all stock is being managed properly. | Update how data is carried over between pages so it isn't lost on going to a new page. | Justin Smith | 3 | 3 | 3 | 0 | 0
| Update save methods and serialization and implement testing. | Justin Smith | 4 | 4 | 4 | 4 | 0
As a Cook, I want to view the inventory so that I can see what food is available. | Create View Inventory Page (FXML document with buttons, listview , other controls, make ViewModel and bind it) | Emi Collins | 6
| Filter View Inventory Page by Role (Tie stock types to roles, implement automatic sorting that only shows allowed stocks for role) | Kirya | 3 | 3 | 3 | 3 | 0
| Create StockType enum | Justin | 4 | 4 | 4 | 2 | 0
| Add time filtering to View Stock Changes page by newest | Justin | 2 | 2 | 2 | 2 | 2
| Add button to home page for view inventory and bind window switching logic | Emi Collins | 1
As a Cook, I want to retrieve food from the inventory to use on the ship. | Adding Removal Business Logic to Button in View Inventory page | Kirya | 4 | 4 | 4 | 4 | 0
As an Officer, I want to view munition stocks to see if the ship is ready for battle. | Filter view Inventory Page to only show munition for officer | Justin | 2 | 2 | 2 | 2 | 2
| Allow Officer to remove munition from inventory | Justin | 2 | 2 | 2 | 2 | 2
| Estimate Totals |  | 24 | 17 | 17 | 15 | 6